## Status
Project |  | TRTS ChangeRequest_06Apr2016
Change Request |  | CRN-TRT-201603-001
Project Manager |  | Atithi Ganjoo
Testing Member |  | Rajeev Singh
| Test Case Count | 0 |  |  |  | Status | Weight
| Total Executed Test Cases | 0 | Executed Tests | Total Tests |  | Passed | >0
| Passed | 0 | 0% | 0% |  | Status | Weight
| Failed | 0 | 0% | 0% |  | Failed | >0
| Blocked | 0 | 0% | 0% |  | Status | Weight
| Pending | 0 | 0% | 0% |  | Blocked | >0
| Not Applicable | 0 | 0% | 0%
PROJECT HIGH LEVEL STATUS
| Testing Schedule Variance | Green
| Testing Effort Variance | Green
| Defects Criticality | Normal
| Defects Priority | Normal
| Defect Density | #DIV/0!
Defect Category
| Functional | Cosmetic | Suggestion | Security
| 0 | 0 | 0 | 0
| Criticality |  |  |  |  | Priority
| Show Stopper | High | Medium | Low | Criticality | Immediate | At Earliest | Normal | Low | Priority
| 0 | 0 | 0 | 0 | Normal | 0 | 0 | 0 | 0 | Normal
Present Status of Defects
| Status | Substatus | [5 empty] | Total Test Cases | Defect Denesity
| Open | New | Closed internally | To be discussed | More Info Required | Change Status | To be fixed Later | 0 | #DIV/0!
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| Re-opened | Not Fixed | Seeded Bug
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| Resolved | Fixed | Not a bug | Duplicate | As Designed | No Plan To Fix | Software Limitations
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| Closed | Fixed | Not a bug | Duplicate | As Designed | No Plan To Fix | Software Limitations
| 0 | 0 | 0 | 0 | 0 | 0 | 0

## Test Plan
Author | Rajeev Singh | Reviewer
Role | Name | Responsibility
Project Manager | Madhup Narula | Project Management
Testing Manager | Adrian Anand Pinto | Test Management
Technical Lead | Rajeev Singh | Test Plan, Test Schedule
Team Member | Rajeev Singh | Test Design,Bug Management,RTM,Test Execution and Bug Reporting
Features/ Functionality to be tested
Features not to be tested
Any existing feature which is not impacted
Entry Criteria
Requirement doc is prepared, Test suite is prepared
Exit Criteria
All test case has been executed and client is agreed upon to stop testing.
Test Deliverables and Acceptance Criteria
Test suite
Risk Tracker
Risk Status | Brief Description |  | Risk Category | Probability | Impact | Risk Exposure | Risk Start Date | Risk Expire Date | Mitigation/Contigency Plan |  |  |  | Remarks
[9 empty] | Action Description | Responsibility | Planned Start Date | Planned End Date
Open | Requirement could be Incomplete/Too highlevel. |  | Schedule | 3 | 4 | 12 | 2016-04-06 | 2016-04-06 | NA | NA | NA | NA | Not required
Open | Scope of testing could be change |  | Schedule | 2 | 5 | 10 | 2016-04-06 | 2016-04-06 | NA | NA | NA | NA | Not required
Note on F38: Author: Refer Guideline for Risk Management
Note on G38: Author: Risk Probability should be value 1-5. Refer Guidelines for Risk Mgmt
Note on H38: Author: Risk Impact should be value 1-5. Refer Guidelines for Risk Mgmt
Note on I38: If RISK EXPOSURE >15 Then Create Risk Mitigation Plan
Note on L38: Author: When Exposure Value is greater than15, plan for Mitigation Plan

## Schedule
Author |  | Rajeev Singh |  | Reviewer
Planned Schedule
|  |  | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr
S.No. | Activity |  | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed
|  | Total hours | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | Project Analysis and understanding | 0
2 | Test Plan Preparation | 0
3 | Test Schedule Preparation | 0
4 | Test Case Preparation | 0
5 | Test case Review/Update | 0
6 | Test Case Execution | 0
7 | Retesting 1 | 0
8 | Regression 1 | 0
9 | Retesting 2 | 0
10 | Regression Testing 2 | 0
11 | Retesting 3 | 0
12 | Regression 3 | 0
13 | Testing Closure and Documentation | 0
14 | Buffer | 1
| Total | 1
Actual Schedule
|  |  | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr
S.No. | Activity |  | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed
|  | Total hours | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | Project Analysis and understanding | 0
2 | Test Plan Preparation | 0
3 | Test Schedule Preparation | 0
4 | Test Case Preparation | 0
5 | Test case Review/Update | 0
6 | Test Case Execution | 0
7 | Retesting 1 | 0
8 | Regression Testing 1 | 0
9 | Retesting 2 | 0
10 | Regression Testing 2 | 0
11 | Retesting 3 | 0
12 | Regression 3 | 0
13 | Testing Closure and Documentation | 0
14 | Buffer | 1
| Total | 1
Daily Variance Tracker | bar: Wed 6 to Sun 10
| Dates | Planned task | Time(hrs) | Actual Task | Time(hrs) | Reason for deviaition | Deviaition (Hrs)
| 2016-04-06 | Closure | 2 | Regression | 2 | Bugs found | 2
Effort Variance
ID | Task | Planned Effort (hours) | Revised Effort (hours) | Actual Effort (hours) | Effort Variance (%) | Effort Variance wrt Revised Effort (%) | Effort exceeded > 5 % | Remarks
1 | Project Understanding | 0 | 0 | 0 | 0 | 0 | No
2 | Test Plan Preparation | 0 | 0 | 0 | 0 | 0 | No
3 | Test Schedule Preparation | 0 | 0 | 0 | 0 | 0 | No
4 | Test Case Preparation | 0 | 0 | 0 | 0 | 0 | No
5 | Test case Review/Update | 0 | 0 | 0 | 0 | 0 | No
6 | Test Case Execution | 0 | 0 | 0 | 0 | 0 | No
7 | Retesting 1 | 0 | 0 | 0 | 0 | 0 | No
8 | Regression Testing 1 | 0 | 0 | 0 | 0 | 0 | No
9 | Retesting 2 | 0 | 0 | 0 | 0 | 0 | No
10 | Regression Testing 2 | 0 | 0 | 0 | 0 | 0 | No
11 | Retesting 3 | 0 | 0 | 0 | 0 | 0 | No
12 | Regression 3 | 0 | 0 | 0 | 0 | 0 | No
13 | Testing Closure and Documentation | 0 | 0 | 0 | 0 | 0 | No
14 | Buffer | 1 | 1 | 1 | 0 | 0 | No
| Total | 1
Schedule Variance
| Phase | Planned Start Date (MM/DD/YYYY) | Planned End Date (MM/DD/YYYY) | Revised Start Date (MM/DD/YYYY) | Revised End Date (MM/DD/YYYY) | Actual Start Date (MM/DD/YYYY) | Actual End Date (MM/DD/YYYY) | No. of days slipped from the Planned End Date | No. of days slipped from the Revised End Date | Duration (in days) | Schedule Variance (%) | Schedule Variance wrt to Revised End Date(%) | Timelines exceded >10 %
| Project Understanding | 2016-04-06 | 2016-04-06 | 2016-04-06 | 2016-04-06 | 2016-04-06 | 2016-04-06 | 0 | 0 | 1 | 0 | 0 | No
| Test Plan Preparation | 2016-04-06 | 2016-04-06 | 2016-04-06 | 2016-04-06 | 2016-04-06 | 2016-04-06 | 0 | 0 | 1 | 0 | 0 | No
| Test Schedule Preparation |  | Mon 11: FALSE; Tue 12: FALSE; Wed 13: 0 | #DIV/0! | #DIV/0! | NA
| Test Case Preparation |  | Mon 11: FALSE; Tue 12: FALSE; Wed 13: 0 | #DIV/0! | #DIV/0! | NA
| Test case Review |  | Mon 11: FALSE; Tue 12: FALSE; Wed 13: 0 | #DIV/0! | #DIV/0! | NA
| Test Case Execution |  | Mon 11: FALSE; Tue 12: FALSE; Wed 13: 0 | #DIV/0! | #DIV/0! | NA
| Retesting 1 |  | Mon 11: FALSE; Tue 12: FALSE; Wed 13: 0 | #DIV/0! | #DIV/0! | NA
| Regression Testing 1 |  | Mon 11: FALSE; Tue 12: FALSE; Wed 13: 0 | #DIV/0! | #DIV/0! | NA
| Retesting 2 |  | Mon 11: FALSE; Tue 12: FALSE; Wed 13: 0 | #DIV/0! | #DIV/0! | NA
| Regression Testing 2 |  | Mon 11: FALSE; Tue 12: FALSE; Wed 13: 0 | #DIV/0! | #DIV/0! | NA
| Retesting 3 |  | Mon 11: FALSE; Tue 12: FALSE; Wed 13: 0 | #DIV/0! | #DIV/0! | NA
| Regression Testing 3 |  | Mon 11: FALSE; Tue 12: FALSE; Wed 13: 0 | #DIV/0! | #DIV/0! | NA
| Testing Closure and Documentation |  | Mon 11: FALSE; Tue 12: FALSE; Wed 13: 0 | #DIV/0! | #DIV/0! | NA
| Buffer |  | Mon 11: FALSE; Tue 12: FALSE; Wed 13: 0 | #DIV/0! | #DIV/0! | NA
Actual Schedule
|  |  | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct
S.No. | Activity |  | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat
|  | Total hours | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | Project Understanding | 1 | bar: Thu 13
2 | Test Plan Preparation | 1 | bar: Thu 13
3 | Test Schedule Preparation | 1 | bar: Thu 13
4 | Test Case Preparation | 56 | Fri 14: 8; Mon 17: 8; Tue 18: 8; Wed 19: 8; Thu 20: 8; Fri 21: 8; Mon 24: 8
5 | Test case Review/Update | 8 | Thu 20: 4; Fri 21: 4
6 | Test Case Execution | 0
7 | Retesting Testing 1 | 0
8 | Regression Testing 1 | 0
9 | Retesting 2 | 16 | Fri 9: 8; Wed 14: 8
10 | Regression Testing 2 | 32 | Thu 15: 8; Fri 16: 8; Mon 19: 8; Tue 20: 8
11 | Testing Closure and Documentation | 0
12 | Buffer | 2
| Total | 117
Formulas:
Schedule Variance (%) = ([Apr]/(NETWORKDAYS([Rajeev Singh],[Apr]))*100)

## ChangeRequests (hidden)
Change Requests v1.0
2015-09-07
1. Job family should appear in View job request pop-up and in email alerts.
2. Link from My Request page of recruiter to Update Candidate Information page directly.
3. Job status should be change able to ‘Declined’ and ‘Revoked’ after “Offer Extended“ as well as “Offer Accepted”.
4. After the status is changed to “Joined”, the drop down should be blocked and should not allow further change of status.
5. ORC field (required for Pre-screening form) should be added under Joining details section. Management to be on TAAdmin Master Data Management section.
6. Add ”Reason to Decline” to Update Candidate Information page.
7. View job request pop-up should show all the candidate names selected corresponding to the job request.
8. Change the nomenclature of “Global Operation Head” to “Hiring Approver”.

## Scope & Effort (hidden)
Screen name | No of VTC approx | No of BTC approx | Total effort in Hours
Generate offer letter | 150 | 100 | 25
Dashboard/ offer letter list | 50 | 80 | 13
Report - Refferel Candidate | 30 | 40 | 7
Report -Candidate joining report | 30 | 40 | 7
Update Candidate information(Interface testing with TRTS) | 10 | 10 | 2
Prescreening reports generation | 5 | 5 | 1
Offer letter and Employee agreement reports | 10 | 10 | 2
Total | 285 | 285 | 57
Items not to be tested
Any flow of TRTS before 'Update Candidate Information' page.

## Validation_Test Cases
Author |  | Rajeev Singh |  |  | Reviewer
Test Case Counts
Total Test Cases |  | 0 | Executed Tests | Total Tests
| Passed | 0 | 0% | 0%
| Failed | 0 | 0% | 0%
| Blocked | 0 | 0% | 0%
| Pending | 0 | 0% | 0%
| Not Applicable | 0 | 0% | 0%
ID | Test Case | Req. ID | Prerequisites | Steps | Input Data | Expected Result | Actual Result | Status | Bug Id
Generate Offer Letter Screen

## Business_Test Cases
Author |  | Rajeev Singh |  |  | Reviewer
Test Case Counts
Total Test Cases |  | 0 | Executed Tests | Total Tests
| Passed | 0 | 0% | 0%
| Failed | 0 | 0% | 0%
| Blocked | 0 | 0% | 0%
| Pending | 0 | 0% | 0%
| Not Applicable | 0 | 0% | 0%
ID | Test Case | Req. ID | Prerequisites | Steps | Input Data | Expected Result | Actual Result | Status | Bug Id | Bug Id

## Requirement missing (hidden)
Template of international offer letter
Template of campus hire
Salary calculation algorithm

## Regression BTC
Author |  | Rajeev Singh |  |  | Reviewer
Test Case Counts
Total Test Cases |  | 0 | Executed Tests | Total Tests
| Passed | 0 | 0% | 0%
| Failed | 0 | 0% | 0%
| Blocked | 0 | 0% | 0%
| Pending | 0 | 0% | 0%
| Not Applicable | 0 | 0% | 0%
ID | Test Case | Req. ID | Prerequisites | Steps | Input Data | Expected Result | Actual Result | Status | Bug Id | Bug Id of 1st testing | Bug ID Regression

## RTM
Author |  | Reviewer
Baseline Requirement Document and Section | System Requirements | System Test Case Id

## Defect Report
ID | Description | Project | Category | Reported By | Reported On | Priority | Severity | Assigned To | Status | Substatus | Defect Type | Phase Injection | Phase Detection | Root Cause | Re-Opened | Last Updated By | Last Updated On

## TCs review log
Reviewer |  | Rajeev Singh
Total review comments |  |  | 0
S. No. | Status | Raised Date | Defect/Issue Description | Requirement ID | Location of Defect | Proposed Resolution | Severity | Defect Type | Defect Disposition | Resolution Owner | Planned Resolved Date | Actual Resolved Date | Reason / Comments | Location of Attachments/ Supporting Documents (if any)